## Initial Timeline(17.03.2023)
Project Virtual prospection(draft)
Project Planner: Sasha Stepanov
Review Date:
Delivery Date:
Phase | Tasks / Activity | Estimated Time (hrs) | Actual Time (hrs) | Target Date of Completion | Actual Date Completion | Variance (hrs)
Empathise | View the Project Details and size of a Scope | 1
| Prepare Questionnaire for the Client Interview | 1 | 1
| Interview with the Client | 1 | 0.4
| Document Client's Interview | 1 | 2
| Follow-up interview with the Client | 0.5
Define | Analyse the Gathered Information
Prepare the Project Proposal
Define the Scope and Requirements of the Project
Create and identify Users
| Research the appropriate Project Management Framework to use | 0.5 | 0
Create the Project Plan, Timetable, Burndown Chart
Plan and Perform Risk Analysis
Plan the Tests for Quality Assurance
Identify the Ethical considerations
Finalise and submit Project Proposal Documentation
Ideate | Ideation process (Generate and refine ideas)
Create Navigation Map for the website
Sketch an initial user interface
Determine the Design Features and Specification of the product
Gather the media assets / 360 pictures for Virtual Tour
Lo-fi Prototyping / Testing | Interview users
Create Wireframe for the Website
Create Wireframe for the Virtual Tour
Implement and pass the Functional Testing
Implement Usability Test with Target Users
Analysed the result of the Usability Testing
Refine and Improve Prototype based on the Testing Results
Finalise the Lo-fi Prototype For the Website and Virtual Tour
Perform and re-evaluate Risk Assessment
Document and submit Design Specification Draft
Hi-fi Prototyping / Testing | Prepare all the media elements that will be used in the Website and Virtual Tour
Create Hi-fi Prototype for the Website and Virtual Tour
Implement and pass the Functional Testing
Implement Usability Test with Target Users
Refine and Improve Prototype based on the Testing Results
Plan the improvement for the next iteration.
Hi-fi Prototyping / Testing | Create the high-fidelity prototype of the Virtual Tour in Lapentor
Create the high-fidelity prototype of the website in ReactJs
Hi-fi Prototyping / Testing | Implement and pass the Functional Testing for website and virtual tour
Implement Usability Test with Target Users for website and virtual tour
Refine and Improve Prototype based on the Testing Results
Finalise the Hi-fi Prototype for the Virtual Tour
Prepare for the presentation of the Hi-fidelity prototype to the Client
Finalise and Deliver the Documentation of the Prototyping and Testing
Deliver an early version of the Website and Virtual Tour
Product Implementation / Testing | Perform and Re-evaluate Risk Assessment
Refinement of the Website Features and Functionality
Refinement of the Virtual Tour Features and Functionality
Final Functionality Testing
Final Usability Testing with Users
Create the Final Specification for the Product
Quality assurance implementation
Create Poster for the Project
Poster Documentation
Project Documentation
Submit all the deliverables and documentation
Deploy a functional and usable final product
| Total time |  |  |  | Total Variance