## Initial Timeline(17.03.2023)
Project Virtual prospection(draft)
Project Planner: Sasha Stepanov
Review Date: TBA
Delivery Date: TBA
Phase | Tasks / Activity | Estimated Time (hrs) | Actual Time (hrs) | Target Date of Completion | Actual Date Completion | Variance (hrs)
Empathise | View the Project Details and size of a Scope | 1 | 1 | 2023-03-01 | 2023-03-01 | 0
| Prepare Questionnaire for the Client Interview | 1 | 1 | 2023-03-03 | 2023-03-03 | 0
| Interview with the Client | 1 | 0.4 | 2023-03-08 | 2023-03-08 | 0.6
| Document Client's Interview | 1 | 1 | 2023-03-10 | 2023-03-10 | 0
| Follow-up interview with the Client | 0.5 |  | TBA | TBA | 0.5
Define | Analyse the Gathered Information | 2 | 2 | 2023-03-15 | 2023-03-15
| Prepare the Project Proposal | 3 | 3 | 2023-03-28 | 2023-03-28
| Define the Scope and Requirements of the Project | 0.5 | 1 | 2023-03-15 | 2023-03-15
| Create and identify Users | 1 | 1.5 | 2023-03-22 | 2023-03-22
| Research the appropriate Project Management Framework to use | 0.5 | 0 | 2023-03-15 | 2023-03-15
| Create the Project Plan, Timetable, Burndown Chart | 1 | 2 | 2023-03-30 | 2023-03-30
| Plan and Perform Risk Analysis | 1 | 0.5 | 2023-03-05 | 2023-03-05
| Plan the Tests for Quality Assurance | 2 | 3 | 2023-03-30 | 2023-03-30
| Identify the Ethical considerations | 2 | 2 | 2023-03-29 | 2023-03-29
| Finalise and submit Project Proposal Documentation | 2 | 3 | 2023-03-15 | TBA
Ideate | Ideation process (Generate and refine ideas) |  |  | TBA | TBA
| Create Navigation Map for the website |  |  | TBA | TBA
| Sketch an initial user interface | 2 | 2 | TBA | TBA
| Determine the Design Features and Specification of the product | 1 | 1.5 | TBA | TBA
| Gather the media assets / 360 pictures for Virtual Tour | 2 | 2 | TBA | TBA
Lo-fi Prototyping / Testing | Interview users | 3 |  | TBA | TBA
| Create Wireframe for the Website | 2 |  | TBA | TBA
| Create Wireframe for the Virtual Tour | 2 |  | TBA | TBA
| Implement and pass the Functional Testing | 3 |  | TBA | TBA
| Implement Usability Test with Target Users | 1 |  | TBA | TBA
| Analysed the result of the Usability Testing | 2 |  | TBA | TBA
| Refine and Improve Prototype based on the Testing Results | 2 |  | TBA | TBA
| Finalise the Lo-fi Prototype For the Website and Virtual Tour | 2 |  | TBA | TBA
| Perform and re-evaluate Risk Assessment |  |  | TBA | TBA
| Document and submit Design Specification Draft |  |  | TBA | TBA
Hi-fi Prototyping / Testing | Prepare all the media elements that will be used in the Website and Virtual Tour |  |  | TBA | TBA
| Create Hi-fi Prototype for the Website and Virtual Tour |  |  | TBA | TBA
| Implement and pass the Functional Testing |  |  | TBA | TBA
| Implement Usability Test with Target Users |  |  | TBA | TBA
| Refine and Improve Prototype based on the Testing Results |  |  | TBA | TBA
| Plan the improvement for the next iteration. |  |  | TBA | TBA
Hi-fi Prototyping / Testing | Create the high-fidelity prototype of the Virtual Tour in Lapentor |  |  | TBA | TBA
| Create the high-fidelity prototype of the website in ReactJs |  |  | TBA | TBA
Hi-fi Prototyping / Testing | Implement and pass the Functional Testing for website and virtual tour |  |  | TBA | TBA
| Implement Usability Test with Target Users for website and virtual tour |  |  | TBA | TBA
| Refine and Improve Prototype based on the Testing Results |  |  | TBA | TBA
| Finalise the Hi-fi Prototype for the Virtual Tour |  |  | TBA | TBA
| Prepare for the presentation of the Hi-fidelity prototype to the Client |  |  | TBA | TBA
| Finalise and Deliver the Documentation of the Prototyping and Testing |  |  | TBA | TBA
| Deliver an early version of the Website and Virtual Tour |  |  | TBA | TBA
Product Implementation / Testing | Perform and Re-evaluate Risk Assessment |  |  | TBA | TBA
| Refinement of the Website Features and Functionality |  |  | TBA | TBA
| Refinement of the Virtual Tour Features and Functionality |  |  | TBA | TBA
| Final Functionality Testing |  |  | TBA | TBA
| Final Usability Testing with Users |  |  | TBA | TBA
| Create the Final Specification for the Product |  |  | TBA | TBA
| Quality assurance implementation |  |  | TBA | TBA
| Create Poster for the Project |  |  | TBA | TBA
| Poster Documentation |  |  | TBA | TBA
| Project Documentation |  |  | TBA | TBA
| Submit all the deliverables and documentation |  |  | TBA | TBA
| Deploy a functional and usable final product |  |  | TBA | TBA
| Total time | 41.5 | 26.9 |  | Total Variance
Maximum budget is 150 hours!!!